# Strategic Planning Committee Board Report

August 6, 2021

Respectfully submitted by: Ryan Hill

Attendees: Robert Wolfe, Leslie Banks, Carrie Smith, Jason Olson, Rownak Ifat, Fay Masterson, Liz Macaulay, Chris Morton, Stephanie Deming, Justin Tosco

Agenda.

- Weighted Lottery update and continued work

- Josie’s Strategic Priorities work and report

- Any near term focus for the committee

Discussion Items.

- Weighted Lottery

  - Expected Timeline

    - Feasibility Study - Fall 2021 for Decision by January 1, 2022

    - If approved, Submission Winter/Spring 2022

    - Approval by DPI by Fall 2022

    - First Weighted Lottery - January 2023

    - First Students from Weighted Lottery start 2023-24 School Year

  - Work Completed

  - Consideration: We need to decide - is this % of incoming students or overall student population?

  - Next Actions

    - Assignments

- Strategic Priorities

  - Vision List

Committee Next Actions.

- Communicate assignments

- Report to status to the board